## Sheet1
Task | Start Date | Days to Complete
Indrocutory and planning (meeting) | 2019-01-22 | 1
Lit. review | 2019-01-23 | 6
Persona Building | 2019-01-23 | 6
Storyboard Design Planning (meeting ) | 2019-01-29 | 1
Storyboards (Iteration 1) | 2019-01-30 | 6
Review of Storyboards (meeting) | 2019-02-05 | 1
Storyboards (Iteration 2) | 2019-02-06 | 2
Presentation of Storyboards | 2019-02-08 | 0.5
Introduction to cozmo | 2019-02-08 | 0.5
Building Cozmo Code (SDK) | 2019-02-09 | 10
Review of Prototype and Cozmo (meeting) | 2019-02-12 | 1
Write Report | 2019-02-12 | 10
Final review of Prototype | 2019-02-19 | 1
Final iteration for development | 2019-02-19 | 2
Presentation (Final) | 2019-02-22 | 1
Review of Group Report (meeting) | 2019-02-22 | 1
Finalise group report | 2019-02-22 | 3
Submission of Group Report | 2019-02-26 | 1
2019-01-22
2019-02-08